## Blad1
Asset List |  | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10
|  |  | PRESENTATIE |  | VACATION
CD_Enemy_Stats | A | WEEK 1: Movement Class; WEEK 2: Wave Class; WEEK 3: Spawning Class | Rief
CD_Enemy_Movement | A | WEEK 1: Basic AI; WEEK 2: Navmesh/A*; WEEK 3: Sounds; WEEK 5: Sounds; WEEK 6: Skybox | Tom
CD_Player_Stats | A | WEEK 1: UI Elements; WEEK 2: Shooting Class; WEEK 3: Particles; WEEK 5: Particles | Arne
CD_Player_Movement | A | Level Design | Level Design | Level Design |  | Level Design | Level Design | Level Design | Level Design | Level Design | Level Design | Thomas
CD_Camera | A | Objects | Objects | Objects |  | Objects | Objects | Objects | Objects | Objects | Objects | Lucas
CD_Shooting | A | WEEK 2: Enemy Animating; WEEK 3: Enemy Texturing; WEEK 5: Pistol Animating
CD_Manager | A | Objects | Objects | Objects |  | Objects | Objects | Objects | Objects | Objects | Objects
CD_WaveSystem | A | WEEK 1: Enemy Modeling; WEEK 2: Pistol Modeling
CD_Wave | A | WEEK 1: Enemy Rigging; WEEK 2: Pistol Texturing
CD_Spawning | A | bar: WEEK 4
CD_Perks | A | bar: WEEK 4
CD_Event_Manager | A | bar: WEEK 4
3D_Enemy | A | bar: WEEK 4
RG_Enemy | A | bar: WEEK 4
AM_Enemy | A | bar: WEEK 4
UV_Enemy | A | bar: WEEK 4
TX_Enemy | A | bar: WEEK 4
3D_Pistol | A | bar: WEEK 4
AM_Pistol | A | bar: WEEK 4
UV_Pistol | A | bar: WEEK 4
TX_Pistol | A | bar: WEEK 4
3D_Broken_Wall | B | bar: WEEK 4
UV_Broken_Wall | B | bar: WEEK 4
TX_Broken_Wall | B | bar: WEEK 4
3D_Broken_House | B
UV_Broken_House | B
TX_Broken_House | B
3D_Barrier | B
UV_Barrier | B
TX_Barrier | B
3D_Crate | B
UV_Crate | B
TX_Crate | B
3D_Barrel | B
UV_Barrel | B
TX_Barrel | B
TX_Grass | A
UI_Healthbar | B
UI_Ammo | B
UI_Score | B
UI_Wave | B
UI_PauseMenu | B
UI_StartMenu | B
3D_Trashcan | B
UV_Trashcan | B
TX_Trashcan | B
3D_Barrier2 | B
UV_Barrier2 | B
TX_Barrier2 | B
3D_Barrier3 | B
UV_Barrier3 | B
TX_Barrier3 | B
3D_Wall | A
UV_Wall | A
TX_Wall | A
3D_Lantern | B
UV_Lantern | B
TX_Lantern | B
3D_TrafficBoard | B
UV_TrafficBoard | B
TX_TrafficBoard | B
3D_TrafficCone | B
UV_TrafficCone | B
TX_TrafficCone | B
3D_BrokenCar | C
UV_BrokenCar | C
TX_BrokenCar | C
TX_Poster | B
3D_TrafficLight | B
UV_TrafficLight | B
TX_TrafficLight | B
3D_Bench | A
UV_Bench | A
TX_Bench | A
3D_SewerLid | C
UV_SewerLid | C
TX_SewerLid | C
3D_Pallet | B
UV_Pallet | B
TX_Pallet | B
3D_Debris | A
UV_Debris | A
TX_Debris | A
3D_PerkMachine1 | C
UV_PerkMachine1 | C
TX_PerkMachine1 | C
3D_PerkMachine2 | C
UV_PerkMachine2 | C
TX_PerkMAchine2 | C
3D_PerkMachine3 | C
UV_ParkMachine3 | C
TX_PerkMachine3 | C
3D_Sandbags | B
UV_Sandbags | B
TX_Sandbags | B
3D_Rocks | A
UV_Rocks | A
TX_Rocks | A
3D_Table | B
UV_Table | B
TX_Table | B
3D_Chair | B
UV_Chair | B
TX_Chair | B
3D_Bricks | A
UV_Bricks | A
TX_Bricks | A
3D_Sofa | C
UV_Sofa | C
TX_Sofa | C
3D_KitchenSink | B
UV_KitchenSink | B
TX_KitchenSink | B
3D_BrokenTable | B
UV_BrokenTable | B
TX_BrokenTable | B
3D_BrokenChair | B
UV_BrokenChair | B
TX_BrokenChair | B
PS_GunFire | A
PS_EnemyHit | A
PS_Fire | B
PS_Dust | B
PS_Cloud | B
PS_Leafs | B
PS_EnvHit | A
PS_Points | B
PS_Pickup | C
3D_Pickup1 | C
UV_Pickup1 | C
TX_Pickup1 | C
3D_Pickup2 | C
UV_Pickup2 | C
TX_Pickup2 | C
3D_Pickup3 | C
UV_Pickup3 | C
TX_Pickup3 | C